## Slide 1: Open Forest Product Roadmap
USDA Forest Service: Open Forest Project
Release Name | Status | Risk | Product Goals
Middle Layer API | Complete |  | Build API that allows data to be passed to SUDS
Special Uses Intake Module | Complete |  | Integrate Open Forest Data to Legacy SUDS (in Dev)
Christmas Tree Module | Complete |  | Build workflows for paying for and printing Christmas Tree permits
MBS NF Special Uses in Beta | In Progress | Low | Pilot forest can use the Open Forest system Non-commercial & temporary outfitter guide permit types are in the Open Forest system
Christmas Tees in Pilot | In Progress | Low | Pilot forests can use the Open Forest system Christmas permits and all critical workflows are in the Open Forest system
MBS NF Special Uses in Production | Committed | Low | Pilot forest can use the Open Forest system within the production environment Non-commercial & temporary outfitter guide permit types are in the Open Forest system
Scale Up to Include Additional Forests | Forecast | Low | Additional forests can use the Open Forest System
Allow More Permit Types | Forecast | TBD | Expand Open Forest Capabilities to include additional permit types
On-Board Additional Forests | Forecast | TBD | All National Forests can use the Open Forest System
Allow More & Extend Business Workflows | Forecast | TBD | Provide the public with more flexible and online options for obtaining permits to use their public lands Reduce the workload for employees involved in the permitting process, so they can spend their time better serving the public, the land, and the agency
SUDS Redesign Integration | Forecast | TBD | Boundaryless information flow b/w Open Forest and next generation SUDS

## Slide 2: In Progress Release Report
USDA Forest Service: Open Forest Project
Release: MBS NF Special Uses In Beta
Delivery Date:
Desired:
August 31, 2018
Forecast:
August 29, 2018
Issues and Pull Requests:
Chart: 
| Remaining | Completed
User Stories & Pull Requests | 6 | 16
Completed
Remaining
16
6
Total Scope:
66 Story Points
Chart: 
| Remaining | Completed
User Stories & Pull Requests | 12 | 54
Completed
Remaining
54
12
Release: Christmas Tree in Pilot
Delivery Date:
Desired:
Nov. 2, 2018
Forecast:
Nov. 2, 2018
Issues and Pull Requests:
Chart: 
| Remaining | Completed
User Stories & Pull Requests | 8 | 1
Completed
Remaining
1
8
Total Scope:
37 Story Points
Chart: 
| Remaining | Completed
User Stories & Pull Requests | 35 | 2
Completed
Remaining
2
35
Terms:
Issues: Analogous to user stories. Documentation of software functionality. Work to be done.
Pull Requests: Code awaiting developer review that fulfill the requirements of issues in the product backlog.
Story Points: Scale of measure for work to be done.
Critical Dependencies:
Approved ATO
USDA email
Pay.gov
Login.gov
Transfer operations to USDA EAS
Outreach and promotion
Notes: # Need a clarifier on issues/PR’s, etc. and what they mean.
# Remove Estimated Scope

## Slide 3: Near-term Forecast
USDA Forest Service: Open Forest Project
Release: Scale Up to Include Additional Forests
Features
Metrics
Key Activities
Public can submit non-commercial, temporary outfitter guide, and Christmas tree permits
Online interaction between customers and USFS special use administrators for applying, review, and issuance of permits
Number of National Forests using the application
Number of permits issues via Open Forest vs. current process
Permit administration time saved
Customer time saved
Outreach and promotion
On-board additional Forests to use Open Forest
Research and design new features (user management workflows, enhanced site navigation, and reporting)

## Slide 4: Product Roadmap Wiki
USDA Forest Service: Open Forest Project

## Slide 5
Release Report (Project GitHub Repository)
USDA Forest Service: Open Forest Project

## Slide 6
Example: Milestone Burndown Report (Project GitHub Repository)
USDA Forest Service: Open Forest Project