## Instructions
INSTRUCTIONS
The Open Forest Product Manager facilitates an annual gap analysis to ensure that the product team has the right skills, resources, tools, and infrastructure to address the highest priority issues the team faces in the course of its ongoing research, design, and development work. Annual gap analyses follow this process:
1 | Using column A in the the scenario template, brainstorm common scenarios that the team encounters and needs to be able to handle in order for the project and product to be successful.
2 | Meet as a team to refine and achieve consensus on the scenarios, making sure that there is a scenario to cover every "showstopper."
3 | As a team, write down success criteria for each of the scenarios: - What does the team need to be able to do in order to handle the scenario? - What skills does the team need to have?
4 | Use the scoring template to assess the priority and team readiness for each scenario
5 | Return to the or each high prioritiy scenario, write down tasks that the team needs to complete in order to ensure that they can meet the success criteria.

## Scenario TEMPLATE
TEMPLATE EXAMPLE
Scenario | Success criteria | Tasks | Notes
A user reports a bug that the team triages as critical. A member of the vendor team files a PR to resolve it. They are able to quickly get the appropriate reviews from team members and push to production using an automated deployment process and without breaking the app. | The app is in production | Verify release process documentation is up to date.
| Users have the ability to report bugs and get them into the queue | Continue to adhere to sprint ceremonies (planning, backlog refinement and grooming).
| At least two members of the team can review and merge Pull Requests without 18F’s help | Ensure that two engineers can view and merge pull requests without help
| There is a shared understanding of the Product Owner’s prioritization | Ongoing collaboration to establish a strong feedback loop with current PO
| The site release process is documented | Ensure that our applications and services are using appropriate authentication credentials.
| The team uses Continuous Development/Continuous Integration pipeline (e.g. github -> circleCi -> cloudFoundryCli -> cloud.gov) | Fill open engineering role.
Ensure that our CI/CD pipelines are documented, well understood, and 2+ people have access.
Scenario | Success criteria | Tasks | Notes

## Scoring TEMPLATE
INSTRUCTIONS: - Copy the scenarios from the scenario sheet and paste them into the success scenario column. - Team members independently score each scenario's priority and the team's readiness to handle it. - Use this sheet to combine everyone's scores (ID# = team member ID or initials). - Sort the TOTAL column from low to high. - Prioritize the scenarioes with the lowest scored scenarios. - Write down tasks that the team needs to complete in order to ensure that they can meet the success criteria for the high priority scenarios, and develop a plan for completing these tasks.
Priority: 1 (needed to succeed), 2 (project may fail), 3 (project OK without) | [5 empty] | Current readiness level: 1 (insuffiencient), 2 (satisfactory), 3 (high)
ID 1 | ID 2 | ID 3 | ID 4 | ID 5 | ID 6 | ID 1 | ID 2 | ID 3 | ID 4 | ID 5 | ID 6 | TOTAL | Success scenario